TizenRT 5.5

Chipset Migration - Execution Plan

Migration of an ARMv8-M chipset product from the 4.0 product branch to the 5.5 product branch,

co-existing with the ARMv8-M BK7239N chipset already supported on 5.5.

| Field | Detail |
| --- | --- |
| Document | Chipset Migration - Execution Plan |
| Target branch | 5.5 product branch (internal) |
| Source branch | 4.0 product branch (internal) |
| Prepared for | Engineering Management Review |
| Date | 22 September 2026 |
| Status | Draft for review |
| Revision | 1.0 |

# Contents

# 1. Objective

Bring the ARMv8-M chipset currently carried on the internal 4.0 product branch onto the internal 5.5 product branch, where it must co-exist with the already-supported ARMv8-M BK7239N chipset, build cleanly, flash through the standard download tooling, and boot and run on the target board.

On the 4.0 branch the chipset uses flat build only, and its BSP sits under the AmebaD tree. The 5.5 product branch today supports loadable build only. Restoring flat build on 5.5 is therefore a hard prerequisite for the port, not a parallel activity.

## 1.1 Deliverables

| # | Deliverable | Dependency |
| --- | --- | --- |
| D-1 | Flat build support restored and proven on the 5.5 product branch | None - starts immediately |
| D-2 | Chipset ported into 5.5, co-existing with BK7239N | Requires D-1 |
| D-3 | Download and flashing tools available for the chipset | Parallel to D-2 |
| D-4 | Product build succeeds and the image boots and runs on the board | Requires D-1, D-2, D-3 |

## 1.2 Out of scope for this phase

- Loadable build support for the migrated chipset (flat is the initial target; see Decision D-1 and Risk R-9).

- Upstreaming the chipset to the public TizenRT repository.

- New feature development on the chipset beyond parity with the 4.0 product branch.

- Secure-side firmware development; the secure image is treated as a prebuilt binary for the first release (see Risk R-6).

# 2. Baseline Findings

The findings below were measured directly against the 5.x code line from which the 5.5 product branch descends. They are the evidence base for the estimates and the sequencing in this plan, and each one is reproducible from the paths cited.

| Finding | Evidence | Why it matters |
| --- | --- | --- |
| Build mode is a Kconfig choice: BUILD_FLAT, APP_BINARY_SEPARATION, BUILD_KERNEL | os/Kconfig lines 188-215 | Flat is a first-class upstream mode. Work on 5.5 is restoration, not invention. |
| APP_BINARY_SEPARATION auto-selects BUILD_PROTECTED, BUILD_2PASS, BINFMT_LOADABLE and LIB_SYSCALL | os/Kconfig lines 200-203 | Flat must bypass the two-pass link, the syscall stubs and binfmt entirely. |
| CONFIG_BUILD_FLAT is referenced in very few files; the real fork in the tree is APP_BINARY_SEPARATION | About 25 references, concentrated in os/mm/mm_heap, os/mm/umm_heap, os/kernel/binary_manager, os/binfmt, os/kernel/task and os/board/common | The flat restoration scope is bounded and locatable. This is the single most encouraging finding for D-1. |
| BK7239N already supports both flat and loadable build | build/configs/bk7239n/Make.defs selects bk7239n_bsp_flat_ns.ld against bk7239n_bsp_loadable_all.ld on CONFIG_BUILD_FLAT; configs hello (flat) and loadable_all | A working reference implementation of flat build on an ARMv8-M chip already exists in the same family. |
| The shared ARMv8-M core carries zero chip-specific conditionals | grep for CONFIG_ARCH_CHIP_ and CONFIG_ARCH_BOARD_ across os/arch/arm/src/armv8-m returns 0 matches | Co-existence is architecturally clean today. Protecting this invariant is the most important design rule of the project. |
| Chip selection is mutually exclusive; both chips resolve to the same ARM family | os/arch/arm/Kconfig lines 84-151: ARCH_CHIP_AMEBAD and ARCH_CHIP_ARMINO both map to ARCH_FAMILY armv8-m | Co-existence means source-level co-existence in one branch, selected per defconfig. The two chips are never compiled together. Expectations must be set accordingly. |
| The flat to loadable configuration delta is small and mechanical | rtl8721csm hello against loadable_apps: BUILD_2PASS, BINARY_MANAGER, BINFMT_*, LIB_SYSCALL, COMPRESSED_BINARY, HEAP_INDEX_LOADED_APP, KMM_REGIONS (2 against 3), RAM_KREGIONx_SIZE, and the FLASH_PART_NAME / SIZE / TYPE triple | Gives an exact defconfig template for the new flat configuration. |
| MPU region counts differ between the two chips | CONFIG_ARMV8M_MPU_NREGIONS is 16 for BK7239N and 8 for AmebaD | Per-configuration, so no conflict in flat build. But 8 regions is tight if loadable is ever required on the migrated chipset. |
| The download framework is pluggable | build/configs/common_download.sh sources a per-board script exposing pre_download, board_download and post_download, plus board_metadata.txt and os/.bininfo | Tooling work is additive and carries low regression risk, so it can run in parallel. |
| The post-build chain has clearly separated loadable-only stages | os/Makefile.unix lines 560-615: PREPARE_APP (loadable only), signing, MAKE_BOARD_SPECIFIC_BIN, MAKE_SAMSUNG_HEADER, set_bininfo.py, convert_binary.py, MAKE_BOOTPARAM, validate_output.py | The flat path must skip the application-binary stages cleanly. |
| BSP payloads in this family are large | AmebaD BSP is 50 MB across 575 files; BK7239N BSP is 139 MB across 6054 files | The migration payload is a full vendor SDK drop, not a patch. This drives the Phase 3 estimate and the repository storage policy. |
| Boards legitimately reuse generic Kconfig symbol names | FLASH_SIZE and FLASH_START_ADDR are each defined by six boards, every one wrapped in an ARCH_BOARD guard in os/board/Kconfig | Symbol collision is a known and solved pattern. Following it exactly avoids type-redefinition warnings. |

# 3. Decisions to Lock Before Coding

These four decisions determine the shape of the entire project and should be signed off in writing at the Phase 0 gate. Decision D-1 is effectively irreversible once BSP migration begins.

## 3.1 D-1: Chip identity - new chip directory or extend AmebaD

| Option | When it is right | Cost |
| --- | --- | --- |
| A. New chip directory under os/arch/arm/src with its own ARCH_CHIP symbol (recommended) | The silicon is a different part that merely reused the AmebaD BSP tree as a 4.0 starting point | Slightly more skeleton work in Phase 2, in exchange for clean upstream merges for the life of the product |
| B. Add a second option inside the existing AmebaD chip choice, alongside ARCH_CHIP_RTL8721CSM | The silicon is genuinely an AmebaD or RTL87xx family derivative | Less new code, but permanent coupling to upstream AmebaD churn |

Recommendation: do not overload the existing amebad directory for a non-AmebaD part. On 5.5, CONFIG_ARCH_CHIP set to amebad already resolves to RTL8721CSM. Overloading it will collide on Kconfig symbols and will make every future rebase onto upstream painful.

## 3.2 D-2: Flat build proven on BK7239N first

Restore flat build on BK7239N, not on the migrated chipset. If the flat path on 5.5 has rotted, that is discovered on hardware that already boots, which separates the question "is flat broken?" from the question "is my port broken?". This is the highest-leverage sequencing decision in the plan and it produces a demonstrable milestone around week five.

## 3.3 D-3: Migration by three-way diff, not directory copy

The 4.0 chipset tree contains chipset code and 4.0-era kernel and framework code, entangled. The migration must first isolate the genuine chipset delta:

delta_chip = diff( 4.0_product_chipset_tree , 4.0_baseline )

and then replay that delta onto 5.5. A straight directory copy imports 4.0 kernel APIs into 5.5, and the team will spend weeks unpicking it later under schedule pressure.

## 3.4 D-4: Vendor code isolation through an adapter layer

Vendor SDK sources stay byte-identical wherever possible, and all TizenRT adaptation lives in a dedicated adapter layer. BK7239N already demonstrates this pattern in os/board/bk7239n/src/bsp_adapter. Reusing that structure keeps future vendor SDK refreshes to a drop-in replacement rather than a re-port.

# 4. Phased Execution Plan

| Phase | Work | Duration | Exit criteria |
| --- | --- | --- | --- |
| P0 | Baseline, gap analysis, decisions D-1 to D-4, toolchain spike | 1-2 weeks | Gap report and signed decision record; vendor SDK compiles standalone with the 5.5 toolchain |
| P1 | Flat build restoration on 5.5, proven on BK7239N | 2-3 weeks | Flat configuration builds and boots on a BK7239N board; loadable build unchanged |
| P2 | Chip and board skeleton registration for the migrated chipset | 1-2 weeks | menuconfig clean with both chips present, zero Kconfig warnings; build reaches link stage |
| P3 | BSP and vendor SDK migration plus API modernisation (critical path) | 4-8 weeks | Kernel links; boots to the TASH prompt on the board |
| P4 | Download and flashing tooling (runs parallel to P3) | 2 weeks | A blank board can be flashed from scratch and boots |
| P5 | Bring-up and functional validation | 3-4 weeks | Test and acceptance matrix in section 6 passing |
| P6 | Co-existence hardening, CI matrix, documentation, handover | 2 weeks | CI green for flat and loadable across all boards; no regression on BK7239N |

Indicative calendar: 13 to 17 weeks, roughly three and a half to four months, with P4 parallelised, assuming two to three engineers and hardware available from P3 onward.

# 5. Workstream Detail

## 5.1 Phase 1 - flat build restoration touch points

| Area | Files and symbols |
| --- | --- |
| Kconfig | os/Kconfig - restore BUILD_FLAT within the Memory organization choice |
| Build flow | os/Makefile.unix - pass1 and pass2 bypass when BUILD_2PASS is unset; post target guards on APP1_INFO, APP2_INFO and SUPPORT_COMMON_BINARY |
| Memory | os/mm/umm_heap and os/mm/mm_heap - single-heap flat path, CONFIG_KMM_REGIONS |
| Kernel | os/kernel/binary_manager, os/binfmt, os/kernel/task, os/kernel/task_monitor, os/kernel/init - APP_BINARY_SEPARATION guards |
| Partitions | os/board/common/partitions.c and os/board/common/Kconfig - flat table without app1 and app2 entries |
| Post-build | os/tools: mkbinheader.py, mkbootparam.py, mkchecksum.py, set_bininfo.py, validate_output.py |
| Board layer | build/configs/bk7239n/Make.defs linker-script switch, scripts flat linker script, new flat defconfig |
| User space | framework/src/binary_manager, apps/system/utils, loadable_apps - must degrade cleanly in flat mode |

## 5.2 Phase 2 - registration checklist

os/arch/arm/Kconfig        config ARCH_CHIP_<X>  (select ARCH_HAVE_MPU, ARCH_CORTEXM33, ...)

config ARCH_CHIP default "<chip>" if ARCH_CHIP_<X>

if ARCH_CHIP_<X> / source arch/arm/src/<chip>/Kconfig / endif

os/arch/arm/src/<chip>/    Kconfig, Make.defs, start, irq, serial, timerisr, idle,

lowerhalf, flash, reboot_reason, systemreset

os/arch/arm/include/<chip>/

os/board/Kconfig           config ARCH_BOARD_<X>, ARCH_BOARD default, source board/<board>/Kconfig

os/board/<board>/          Kconfig (wrapped in if ARCH_BOARD_<X>), Kconfig.signing,

include/board.h, src/{Make.defs, Makefile, boot.c}

build/configs/<board>/     Make.defs, board_metadata.txt, make_bin.sh, download.sh,

signing.sh, scripts linker scripts, defconfig

## 5.3 Phase 4 - download and flashing tooling

- Vendor host tools under build/tools, following the AmebaD reference layout: image_tool, gnu_utility and the fixed and dynamic partition bootloader binaries.

- A per-board download script implementing the pre_download, board_download and post_download hooks expected by build/configs/common_download.sh.

- board_metadata.txt providing BOARD, DEFAULT_PORT, BL1, BL2, KERNEL, OTA and BOOTPARAM names.

- Verification that the 5.5 common download script handles a flat partition table with no app1 or app2 entries. This is very likely an untested path on a loadable-only branch and should be treated as real work, not a check.

- USB rule and udev setup, Python dependencies, and the DOWNLOAD macro in the board Make.defs.

# 6. Risk Register

| # | Risk | Sev | Mitigation |
| --- | --- | --- | --- |
| R-1 | The extent of flat-path rot on 5.5 is unknown until branch access is granted | High | Timeboxed Phase 0 spike; running Phase 1 on BK7239N isolates the variable from the port |
| R-2 | The 4.0 BSP drags 4.0 kernel APIs into 5.5 | High | Decision D-3 three-way diff, adapter layer, and an explicit no-blind-copy rule |
| R-3 | 4.0 code patched the shared ARMv8-M core, causing BK7239N regressions | High | Hold the zero-chip-conditionals invariant; express differences as Kconfig features such as ARMV8M_HAVE_DCACHE; regression-build BK7239N on every commit |
| R-4 | Toolchain divergence between the 4.0-era compiler and 5.5, covering cmse, FPU ABI and newlib | High | Pin the toolchain in Phase 0 and make compiling the vendor SDK with the 5.5 toolchain the Phase 0 exit gate |
| R-5 | Network stack version jump across lwIP, netmgr and the WiFi manager API | High | Treat as its own sub-workstream inside Phase 3 and Phase 5 with explicit budget, rather than absorbing it into driver work |
| R-6 | Secure and TrustZone model mismatch; BK7239N uses a TF-M based flow while AmebaD uses NSC veneers | Medium | For the first release keep the secure image as a prebuilt binary; add a dedicated secure-element backend under os/se later |
| R-7 | Repository bloat and licensing exposure from a 50 to 140 MB vendor binary drop | Medium | Agree the storage and licence policy in Phase 0, including whether large binaries go in-tree or to LFS |
| R-8 | Bootloader, header or partition mismatch, where the existing bootloader expects the 4.0 header format | Medium | Decide the header and boot-parameter strategy in Phase 0; validate_output.py catches size faults early |
| R-9 | MPU budget of 8 regions may not support loadable build later | Medium | Confirm the silicon region count in Phase 0 and scope loadable build as an explicit future phase rather than an assumption |
| R-10 | Regression to the existing 5.5 loadable boards | Medium | CI matrix covering flat and loadable across every board, gating every merge |
| R-11 | Board and debug probe availability slips Phase 3 to Phase 5 | Medium | Secure boards and JTAG or SWD probes before Phase 3 starts, not when it starts |
| R-12 | Kconfig symbol type collisions between the two chips | Low | Follow the existing guard pattern exactly for both the board and the chip Kconfig files |

# 7. Test and Acceptance Matrix

| Level | Check |
| --- | --- |
| Build | New board flat; BK7239N flat; BK7239N loadable; all other 5.5 boards, with no regression |
| Static | menuconfig clean with zero warnings while both chips are present; validate_output.py passes; binary fits its partition |
| Boot | Console and UART up; tick and timer running; heap and MPU initialised; boots to the TASH prompt |
| Peripheral | UART, SPI, I2C, flash and MTD, RTC, watchdog, GPIO |
| Storage | SmartFS mount, read and write; resource filesystem if used by the product |
| Network | WiFi scan, connect and DHCP; the nettest suite |
| System | Reboot reason, crash dump, power and sleep modes, and OTA if in scope |
| Regression | Kernel test-case suite; BK7239N board sanity re-run after every merge |
| Tooling | Full flash of a blank board from scratch, plus per-partition download |

# 8. Resourcing and Dependencies

| Role | Allocation | Phases |
| --- | --- | --- |
| Kernel and build engineer | 1.0 FTE | P0 to P2 and P6 - flat restoration, Kconfig and build integration |
| BSP and driver engineer | 1.0 to 1.5 FTE | P0, P3, P5 - vendor SDK, drivers, board bring-up |
| Tools and release engineer | 0.5 FTE | P4 and P6 - download, signing, CI |
| Validation engineer | 0.5 FTE | P5 and P6 |

Hardware: at least three target boards and two debug probes, available before Phase 3 begins.

Access required: the 4.0 product branch, the 5.5 product branch, vendor SDK release notes, and either the bootloader source or its binaries together with the header specification.

# 9. Open Questions

These should be closed during Phase 0. Questions 1, 2 and 5 move the estimate by several weeks in either direction and should be prioritised.

- Is the chipset genuinely AmebaD-family silicon, or an unrelated part that merely reused the AmebaD BSP tree? This drives decision D-1.

- Was flat build removed from 5.5, or is it present but untested? This is the difference between a one-week and a four-week Phase 1.

- Which compiler version does 5.5 standardise on, and does the 4.0 vendor SDK compile with it?

- How many MPU regions does the silicon expose?

- Is loadable build required for this chipset on any roadmap, or is flat the permanent target?

- What are the secure boot, signing and TF-M requirements for the product, and is the secure image a binary or must it be built?

- Is OTA or binary-manager functionality needed in flat mode?

- Which supplicant and lwIP versions does the 4.0 BSP carry?

- What is the repository policy for large vendor binaries, in-tree against LFS?

- What is the board and debug probe availability date?

# 10. Summary and Next Steps

## 10.1 Key findings

- Flat build restoration on 5.5 is bounded and low-risk. CONFIG_BUILD_FLAT has few direct references; the real fork in the tree is APP_BINARY_SEPARATION, concentrated in about six known directories. BK7239N already ships a working flat and loadable reference on ARMv8-M.

- Co-existence is not a technical problem today. The shared ARMv8-M core carries zero chip-specific conditionals, and chip selection is a mutually exclusive Kconfig choice. Co-existence means both ports live in one branch and are selected per defconfig; they are never compiled together. The whole risk lies in keeping that invariant if the 4.0 code patched shared core files.

- The real cost centre is Phase 3, the vendor BSP migration and the 4.0 to 5.5 API modernisation, not the build-mode work. Reference payloads in this family are 50 MB across 575 files and 139 MB across 6054 files.

- Download tooling is additive and pluggable, making it the lowest-risk of the four deliverables and a good candidate for parallel execution.

- Indicative effort is 13 to 17 weeks with two to three engineers across six phases, with hardware required from roughly week five.

## 10.2 Next steps

- Obtain sign-off on decisions D-1 to D-4, and in particular D-1, which is irreversible in practice once BSP migration starts.

- Run the Phase 0 toolchain spike: compile the 4.0 vendor SDK with the 5.5 toolchain. This single experiment retires the highest-severity risk, R-4, within days.

- Answer open questions 1, 2 and 5, which carry the largest estimate variance.

- Confirm board and debug probe availability before Phase 3 starts.

- Begin Phase 1, flat build on BK7239N, immediately. It requires no information about the migrated chipset and produces the first demonstrable milestone.

## 10.3 Recommended framing for management

The work is two dependent projects, not one. Restoring flat build on 5.5 is a kernel and build-system task with bounded, locatable scope that can be proven on BK7239N hardware already in hand. Porting the chipset is a BSP task whose size is driven by a full vendor SDK and a 4.0 to 5.5 API jump. Attempting them together makes every failure ambiguous. Sequencing them delivers a demonstrable milestone around week five and makes the second half estimable with real data rather than assumption.