TizenRT 5.5 Chipset Migration - Plan Summary

ARMv8-M chipset  |  4.0 product branch to 5.5 product branch  |  23 September 2026  |  Draft for review

# 1.  Objective

Migrate the ARMv8-M chipset product from the 4.0 product branch onto the 5.5 product branch, where it must co-exist with the ARMv8-M BK7239N chipset already supported there. The chipset uses flat build; the 5.5 branch today supports loadable build only, so flat build support must be restored on 5.5 before the port can begin.

# 2.  Deliverables

| # | Deliverable | Depends on |
| --- | --- | --- |
| 1 | Flat build support restored and proven on the 5.5 product branch | Nothing - starts immediately |
| 2 | Chipset ported into 5.5, co-existing with BK7239N | Deliverable 1 |
| 3 | Download and flashing tools available for the chipset | Parallel to deliverable 2 |
| 4 | Product build succeeds; image boots and runs on the board | Deliverables 1, 2, 3 |

# 3.  Assessment: the work is lower-risk than it first appears

Verified directly against the 5.x code line from which the 5.5 product branch descends:

- The exact target combination already works upstream. RTL8721CSM runs AmebaD chip plus ARMv8-M plus flat build today. We therefore have a working reference in the chipset’s own BSP family, and a second one on BK7239N. Nothing here is being invented from scratch.

- Flat restoration is bounded and measurable. Only 61 files and 177 lines under os/ carry the flat-versus-loadable fork, and a complete 1,231-line flat configuration template already exists to copy from.

- Co-existence is already clean. The shared ARMv8-M core is 51 files and roughly 9,900 lines with zero chip-specific conditionals. Chip selection is mutually exclusive, so the two chipsets co-exist in source and are never compiled together.

- The real cost is the BSP, not the build system. Vendor BSPs in this family run 50 to 139 MB across 575 to 6,054 files. Phase 3 is the critical path and carries most of the schedule risk.

# 4.  Plan

| Phase | Work | Weeks | Milestone |
| --- | --- | --- | --- |
| 0 | Baseline, gap analysis, key decisions, toolchain spike | 1-2 | Vendor SDK compiles with the 5.5 toolchain |
| 1 | Restore flat build on 5.5, prove it on BK7239N | 2-3 | Flat image boots on hardware already in hand |
| 2 | Register chip and board skeleton for the new chipset | 1-2 | Clean configuration; build reaches link stage |
| 3 | BSP migration and 4.0 to 5.5 API modernisation (critical path) | 4-8 | Boots to shell prompt on the target board |
| 4 | Download and flashing tools (runs parallel to Phase 3) | 2 | Blank board flashed from scratch |
| 5 | Bring-up and functional validation | 3-4 | Test and acceptance matrix passing |
| 6 | Co-existence hardening, CI matrix, documentation, handover | 2 | CI green; no regression on BK7239N |

Total 13 to 17 weeks (about 3.5 to 4 months) with Phase 4 parallelised. First demonstrable milestone at roughly week 5.

# 5.  Top risks

| # | Risk | Impact | Mitigation |
| --- | --- | --- | --- |
| 1 | Extent of flat-build removal on 5.5 is unknown until branch access is granted | High | Timeboxed Phase 0 spike; prove Phase 1 on BK7239N so build-mode failures stay separable from port failures |
| 2 | The 4.0 BSP drags 4.0-era kernel APIs into 5.5 | High | Migrate by three-way diff against the 4.0 baseline rather than copying directories; keep vendor code behind an adapter layer |
| 3 | 4.0 code patched the shared ARMv8-M core, causing BK7239N regressions | High | Hold the zero-conditional invariant; express differences as configuration options; regression-build BK7239N on every commit |
| 4 | Toolchain divergence between the 4.0-era compiler and 5.5 | High | Make compiling the vendor SDK with the 5.5 toolchain the Phase 0 exit gate, before any porting effort is spent |
| 5 | Network stack jump across lwIP, network manager and the WiFi API | High | Budget as its own sub-workstream inside Phases 3 and 5 rather than absorbing it into driver work |

The full twelve-entry risk register, file-level touch points and test matrix are in the detailed plan held on the work branch.

# 6.  Decisions needed from management

- Chip identity. Create a separate chip directory for the new chipset, or extend the existing AmebaD chip option. This is effectively irreversible once BSP migration starts. Recommendation: a separate chip directory, unless the silicon is genuinely AmebaD-family, because overloading the existing one collides with RTL8721CSM and makes every future upstream rebase painful.

- Is loadable build required for this chipset on any roadmap? The silicon may expose only 8 MPU regions against BK7239N’s 16, which constrains loadable feasibility. Flat build is the current target and this plan assumes it stays that way.

- Repository policy for a 50 to 139 MB vendor binary drop: held in-tree, or moved to large-file storage.

# 7.  Resources required

| Role | Allocation | Phases |
| --- | --- | --- |
| Kernel and build engineer | 1.0 FTE | 0 to 2, and 6 |
| BSP and driver engineer | 1.0 to 1.5 FTE | 0, 3 and 5 |
| Tools and release engineer | 0.5 FTE | 4 and 6 |
| Validation engineer | 0.5 FTE | 5 and 6 |

Hardware: at least three target boards and two debug probes, in place before Phase 3 begins at roughly week 5.

Access: the 4.0 and 5.5 product branches, vendor SDK release notes, and the bootloader binaries together with the header specification.

# 8.  Next steps

- Sign off the three decisions in section 6, in particular the chip identity decision.

- Run the Phase 0 toolchain spike. This single experiment retires the highest-severity risk within days.

- Close the two questions carrying the largest estimate variance: was flat build removed from 5.5 or merely left untested, and is the chipset genuinely AmebaD-family silicon.

- Start Phase 1 immediately. It needs no information about the new chipset and lands the first demonstrable milestone at about week 5.