MMU-Based Memory Corruption Detection

Implementation Plan

Sequencing, risk retirement, patch structure and test strategy

| Field | Value |
| --- | --- |
| Project | TizenRT |
| Target platform | rtl8730e / amebasmart, ARM Cortex-A32, SMP (2 cores) |
| Reference config | build/configs/rtl8730e/loadable_ext_ddr |
| Companion document | MMU-Based Memory Corruption Detection - Design Document |
| Scope of this document | How to sequence and deliver the feature |
| Status | Draft for review |

# Table of Contents

# 1. Purpose

The design document explains WHAT to build. This document explains HOW TO SEQUENCE it: which piece comes first, why that order, where the checkpoints are, how the change should be split for review, and what to test at each step.

It exists because the first attempt at this feature was delivered as a single large change, and a foundational problem in the chosen mechanism only surfaced during review, after everything else had been built on top of it. The plan below is arranged specifically so that cannot happen again.

## 1.1 The one-line summary

Prove the mechanism on a throwaway test page first. Then rework the watchdog. Then do the heap. Do not start either real feature until the mechanism is proven and measured.

# 2. The Planning Principle

Order the work by how much risk each step retires per unit of effort - not by feature size, and not by what happens to be written already.

In kernel work the thing that destroys schedules is discovering a foundational problem late, after other work has been layered on top of it. When that happens the cost is not the fix itself; it is that everything built on the broken assumption has to be re-examined at the same time.

The first attempt at this feature is the example. A large change landed, and only at review did it become clear that the underlying mechanism does not work on the SMP configuration the feature was enabled for. The watchdog integration, the linker layout, the heap adjustments and the configuration changes all had to be reconsidered together.

So the rule for this plan is simple: find the unknowns, kill the dangerous ones first with the smallest possible experiments, and only then commit to the bulk work.

Practical consequence:  The first thing built is not a feature at all. It is a test page that exists only to prove the mechanism. That feels like a detour and it is not - it is the cheapest possible way to answer the questions that decide whether the rest of the project is viable.

# 3. Current Status

## 3.1 What exists today

A change adding watchdog MMU protection has been written and reviewed. It provides useful groundwork, but it implements a different mechanism from the one required: it switches a CPU register (DACR) rather than modifying the MMU page table, and it works at 1 MB granularity rather than 4 KB.

When planning, it is important to separate the parts that survive from the parts that must be replaced. The existing work is not wasted, but it is also not a finished watchdog feature.

| Existing element | Verdict |
| --- | --- |
| Analysis of which watchdog functions need write windows | KEEP - the analysis is correct, only placement needs fixing |
| Overall shape of the protection module (init, begin, end, nesting) | KEEP the structure, replace the body |
| Configuration symbol and the idea of a dedicated linker section | KEEP |
| DACR register switching functions | REPLACE with page-table manipulation |
| 1 MB section reserved at a fixed address | REPLACE with a single 4 KB page |
| Linker heap adjustments and the shared ARM heap allocation change | DELETE - not needed once the page is 4 KB |
| Only the timer pool relocated | EXTEND to all four watchdog globals |
| Pre-allocated timer count left unchanged | RAISE to fill the page |
| Write windows opened around read-only operations | REMOVE - reads never needed them |
| Write window held open across timer callbacks | FIX - close it around the callback |

## 3.2 The rework is smaller than it looks

Moving from 1 MB to 4 KB removes work rather than adding it. The 1 MB section is what forced the hard-coded address, the shrinking of the DRAM heap, the adjustment to the shared ARM heap allocation code, and the loss of zero-initialisation caused by placing the data outside the normal cleared region.

A 4 KB page needs none of that. Four of the issues raised in review disappear on their own as a side effect of using the correct granularity.

## 3.3 One thing that cannot be deferred

The register-based mechanism cannot be kept for the watchdog while the page-table mechanism is used for the heap. The register is per-core and is not shared between the two CPUs, so any access to the protected memory from the second core faults - including ordinary reads from the timer tick handler. On the shipping SMP configuration this is a boot-level defect, not a deferred cleanup.

# 4. Code Analysis Findings

Before committing to this plan, the existing kernel, memory-manager and architecture code was read against every milestone. Six findings change the plan. Two of them make the work materially easier.

## 4.1 Finding 1 - a use-after-free detector already exists

The tree already contains a poison-pattern use-after-free detector, complete with its own configuration entries and allocator hooks. It fills a released chunk with a known pattern and verifies the pattern when the chunk is handed out again.

The good half: every hook point this plan needs is already located, wired and shipped. Finding those sites was the largest risk in the heap milestone, and that work is done.

| Existing call site | Corresponds to |
| --- | --- |
| Poison, when a chunk enters the free list | The PROTECT point |
| Verify, when a chunk is handed out by allocation | The UNPROTECT point |
| Verify before forward merge | Unprotect before merging |
| Verify before backward merge | Unprotect before merging |
| Verify before chunk shrink | Unprotect before split |
| Verify before aligned allocation carve | Unprotect before split |
| Verify before reallocation extend | Unprotect before resize |

The bad half: the two features collide. The poison routine writes into the released chunk and the verify routine reads it, so under no-access protection both would fault. The verify failure path is worse still - it dumps the entire node word by word, which is a guaranteed fault.

Recommendation:  Make them complementary rather than exclusive. The poison pattern is clamped to a small number of bytes by configuration, so it naturally covers the small chunks the MMU cannot touch, while page protection covers whole pages of large ones. They partition by size. Sequence protection after poisoning and removal before verification, and teach the dump routine to skip protected ranges.

## 4.2 Finding 2 - zero initialisation is free if the section is placed correctly

The plan assumed the watchdog page would need explicit clearing at start-up, because a no-load section is not cleared automatically. Reading the actual linker script shows this is avoidable.

The symbol marking the end of the cleared region is defined near the end of the stack section, not at the end of the data section. The cleared range therefore spans the uninitialised data, the small heap and the stack. A section placed between the uninitialised data and the heap falls inside that range and is cleared by the start-up code.

The earlier attempt placed its section after the end-of-clear symbol, which is precisely why it lost zero initialisation. Placing the new section correctly removes the need for explicit clearing entirely.

## 4.3 Finding 3 - page table space is nearly exhausted

The architecture header documents its own page table budget: one kernel top-level table, two application top-level tables and twelve second-level tables, totalling sixty kilobytes, rounded up to a sixty-four kilobyte reservation.

That leaves four kilobytes of slack - exactly four spare second-level tables, and under multi-core builds the whole reservation is multiplied by the processor count.

| Option | Consequence |
| --- | --- |
| Use the existing four kilobytes of slack | Only four megabytes of address space can ever be protected, against a heap of roughly sixty megabytes |
| Increase the page table reservation | Straightforward, but touches the memory map and doubles under multi-core |

Four megabytes is enough for the watchdog page and a first heap experiment, but not for meaningful heap coverage. This must be decided during Milestone 0, not discovered during the heap work.

## 4.4 Finding 4 - deferred releases write into the released memory

A release performed from interrupt context is deferred: the released pointer is cast directly to a link node and the link is written into the payload of the block itself.

Protection must therefore not be applied when release is requested, but only when the block actually joins the free list. Since every free node passes through a single function to join that list, protection needs exactly one insertion point rather than one per caller.

## 4.5 Finding 5 - the list removal macro needs no change

Removing a node from the free list only touches the forward and backward link fields, which live in the node header and are never protected. The macro therefore needs no handling at all.

What does need handling is every place a header is written into the middle of a previously free block - the split, shrink, aligned-allocation and reallocation paths. Those are the same sites already carrying the existing verify calls, which is a convenient coincidence.

## 4.6 Finding 6 - a defect in the fault status macros

One of the data fault status macros shifts its mask by another mask instead of by the corresponding shift value, so the domain field it produces is wrong. Nothing uses it today, which is why it has gone unnoticed.

The fault decoder built in Milestone 0 is the first consumer, so the fix belongs in the same commit as the decoder.

# 5. Comparison With Upstream

The kernel, memory manager and architecture code in this tree derive from an upstream real-time operating system project. That project was fetched and compared against this tree for every area the plan touches. The comparison changes the strategic picture in three ways.

## 5.1 Upstream already solves heap corruption detection

Upstream contains a complete address sanitiser subsystem, wired directly into its allocator: the release path poisons, the allocation path unpoisons. It detects use-after-free, buffer overruns and out-of-bounds access at any size, not only in blocks larger than a page.

| Aspect | Upstream sanitiser | Page protection (this plan) |
| --- | --- | --- |
| Granularity | Four-byte granule - catches a small overrun | Four kilobyte page - large blocks only |
| Memory cost | Shadow map of about one thirty-second of the region | One small table per protected megabyte |
| Runtime cost | Every load and store carries a compiler-inserted check | None - the hardware checks anyway |
| Build requirement | Compiler instrumentation flag across the image | None |
| Effort to adopt here | Substantial - the allocators have diverged | Moderate |
| Also detects | Overruns, out-of-bounds, global variables | Only what lies inside a protected page |

Its own configuration help warns that instrumenting the whole image increases size and decreases performance significantly. There is also an optional hardware-watchpoint mode which avoids instrumentation and is worth investigating.

This is a decision, not a detail:  The original question was whether the MMU can be used to debug memory corruption. The honest answer is yes, and upstream also solved it another way. Three tools now exist at three different cost and coverage points - the existing poison detector for small chunks, page protection for large ones, and the upstream sanitiser for everything at a price. The requester should choose knowingly rather than discover the alternative later.

## 5.2 Upstream has page-granular mapping helpers this tree lacks

This is good news for Milestone 0. Upstream provides functions to point a top-level entry at a second-level table and to write second-level entries from a descriptor, together with the descriptor type itself. These are precisely the two halves of the primitive this plan calls for.

The architecture layer can therefore be backported rather than invented, which reduces the largest technical risk and narrows the gap with upstream instead of widening it.

The divergence runs both ways. This tree added application-separation mapping code that upstream does not have; upstream added page-granular mapping that this tree does not have. The architecture file here is roughly half as long again as its upstream counterpart.

## 5.3 The watchdog has diverged completely

Upstream rewrote its watchdog timer. This tree still carries the design from before that rewrite.

| Aspect | This tree | Upstream |
| --- | --- | --- |
| Timing model | Delta list - each entry relative to the one before | Absolute expiry time per entry |
| List type | Custom singly linked queue | Generic doubly linked list node |
| Storage | Pre-allocated static pool plus free list and counter | No pool at all - caller allocated |
| Source files | Eleven | Five |
| Pre-allocated count setting | Exists | Does not exist |

The strategic consequence: the memory this plan protects in the watchdog milestone does not exist upstream and never will. It is an artefact of the older design carried here.

That does not make the milestone wrong. It is small, it is the right pilot, and the divergence it adds is minor beside what already exists. But it should be a conscious decision rather than a side effect, because it raises the cost of any future move towards the upstream watchdog.

## 5.4 The memory manager has diverged in both directions

Thirteen memory-manager source files exist only in this tree, largely the heap information and diagnostic layer plus the existing use-after-free detector. Six exist only upstream. The free node structures differ as well: this tree records a single allocation address and a single release address, while upstream records a sequence number and an optional full call stack.

That divergence is the main reason adopting the upstream sanitiser would be real work rather than a drop-in. It is also an opportunity: upstream records a call stack per allocation, which would improve the fault reports described in this plan far more cheaply than adopting the whole sanitiser.

## 5.5 Effect on the plan

| Milestone | Effect of the comparison |
| --- | --- |
| Milestone 0, architecture | IMPROVED - backport the upstream page-mapping helpers instead of writing new ones |
| Milestone 0, reporting | Consider backporting per-allocation call stacks for richer reports |
| Milestones 1 and 2, watchdog | Unchanged technically, but now an explicit divergence decision |
| Milestones 3 and 4, heap | BLOCKED on a decision - page protection, the upstream sanitiser, or both |
| Milestones 5 and 6 | Unchanged |

Recommendation: proceed with Milestones 0, 1 and 2 as planned, using the upstream helpers where they fit. Pause before the heap milestone and put the choice of detection technology to the requester.

# 6. Risk Register

These are the genuine unknowns. The plan is built around retiring the cheap-to-test ones before committing to the expensive work.

Risk four was downgraded after the code analysis in section 4. A seventh risk was added from the upstream comparison in section 5.

| ID | Risk | Impact if found late | Cost to test early |
| --- | --- | --- | --- |
| R1 | Splitting a live 1 MB mapping into 4 KB pages corrupts the mapping - wrong attribute bits, wrong ordering, or an SMP visibility problem | Fatal. Everything else sits on this. | Low - a unit test comparing all 256 new entries against the original |
| R2 | The fault fires but we cannot produce a report that identifies the culprit | High. The feature delivers protection but no diagnostic value. | Low - one deliberate bad write |
| R3 | Converting large parts of the heap from 1 MB mappings to 4 KB pages degrades performance through address-translation cache pressure | Fatal to the heap feature. May invalidate the whole approach. | Low - split N regions in a test and run a heap benchmark |
| R4 | The allocator cannot survive protect and unprotect around block merging and splitting | Moderate. DOWNGRADED - see finding 1: every hook site already exists and is proven in shipped code. | Moderate - the sites are known, only the sequencing is new |
| R5 | Existing heap walkers, heap information commands and the crash dump path fault on protected pages | Medium. Mechanical to fix but embarrassing if found in the field. | Low - a code audit |
| R6 | Page table reservation has only four kilobytes of slack, capping protectable address space at four megabytes | High. Caps heap coverage far below the heap size. | None - already established, see finding 3. Needs a decision. |
| R7 | A different detection technology already exists upstream and may be preferred | High. Could invalidate the heap half after it is built. | None - already established, see section 5. Needs a decision. |

R1, R2 and R3 are all cheap to test and all block everything downstream. They are therefore the first work item, before either real feature is touched. R4 is the one risk that cannot be de-risked cheaply, so the goal is to enter it with everything else already proven.

# 7. Milestone 0 - The Walking Skeleton

## 7.1 What it is

Before the watchdog and before the heap, build the thinnest possible end-to-end slice against a dummy test page - a 4 KB static array that exists only for this purpose.

test page (4 KB static array, used by nothing else)

|

protect

|

deliberate write from test code

|

*** data abort ***

|

report naming the exact instruction and task

|

unprotect

|

write succeeds normally

No watchdog code. No allocator code. Nothing in this milestone can destabilise the running system, because nothing real depends on the test page.

## 7.2 Why this first

- It retires R1 and R2 completely.

- It is where the R3 measurement is taken, using the same primitive.

- It is roughly five hundred lines in total.

- At the end of it you know whether the whole project is viable, having spent very little.

Everything after this milestone is applying a proven mechanism rather than debugging two unknowns at the same time. That is a fundamentally different risk profile from where the first attempt was operating.

## 7.3 What it contains

| Item | Description |
| --- | --- |
| Page-level protect primitive | Split a 1 MB mapping into 4 KB pages; set one page read-only or no-access; save and restore the original entry. BACKPORT the upstream page-mapping helpers rather than writing new ones - see section 5.2 |
| Generic interface | Architecture-neutral entry points so that kernel and memory-manager code never call architecture-specific functions directly |
| Fault decoding | Decode the fault status and fault address registers; distinguish a permission fault from a translation fault |
| Protected region registry | A small table of registered regions with names, so the fault report can say which region was hit |
| Test application | A deliberate-corruption test that writes to the protected page and confirms the report |
| Performance measurement | Split a number of regions and compare heap benchmark results before and after |
| Page table budget decision | Decide whether to use the four kilobytes of existing slack or to increase the reservation - see finding 3. This caps how much heap can ever be covered. |

# 8. Milestone Sequence

M0  Walking skeleton  ------------------>  GATE 1: mechanism proven?

|- arch: split, set permission, save/restore        -+

|- arch: fault decode, region registry, report       | can run

|- test: dummy page + corruption test app            | in parallel

+- measure: translation-cache and performance cost  -+

M1  Watchdog packing (no protection yet)

|- four globals grouped into one structure, own 4 KB page

|- placed INSIDE the cleared range, so no explicit clearing

+- raise pre-allocated timer count to fill the page

M2  Watchdog protection  ---------------->  GATE 2: first real delivery

|- write windows at the correct call sites

|- no windows around reads; window closed around callbacks

+- SMP test: write from the second core

M3  Heap: free and allocate paths only

+- simplest possible use-after-free catch

M4  Heap: merging, splitting, reallocation, aligned

allocation, deferred free list          <-- THE BIG ONE

M5  Audit: heap walkers, heap info commands, crash dump

M6  Harden: coverage counters, stress, documentation

--->  GATE 3: enable by default

## 8.1 Why M1 and M2 are separate

This separation is worth insisting on. M1 changes no behaviour. It relocates four variables and raises a count. It can be verified entirely on its own: the system boots, timers work, more timers are available, and no protection is involved.

M2 is then a small, focused change on top. If M2 breaks something, M1 is not a suspect. If M1 breaks something, it is found before any protection logic exists to confuse the picture.

The first attempt bundled these together, which is part of why the review had to separate layout problems from mechanism problems by hand.

## 8.2 Why the watchdog comes before the heap

- Groundwork already exists and much of the analysis is reusable.

- The watchdog module has a closed set of accessors, so every legitimate access can be wrapped with confidence.

- It is small enough to complete quickly and demonstrate.

- The heap work is much larger and riskier, and benefits from starting on a foundation that has already run in a real subsystem.

## 8.3 A risk to manage with this order

Be candid about one thing: the watchdog pool is probably not where the actual corruption is happening.

It is the right pilot - small, closed, easy to reason about. But if watchdog protection ships and nothing is caught for two months, the natural conclusion will be that the feature does not work. That would be the wrong conclusion.

State the framing explicitly in progress reports: the watchdog milestone proves the mechanism works; the heap milestone is where bugs actually get caught. This costs nothing now and protects the project later.

# 9. Decision Gates

A gate is a point where work stops and a question is answered before more is invested. Gate 1 is the checkpoint the first attempt did not have.

| Gate | After | Question | If the answer is no |
| --- | --- | --- | --- |
| 1 | M0 | Does splitting a live mapping work correctly? Does the report name the culprit? Is the performance cost acceptable? | Stop. Reconsider the approach before spending anything on either consumer. |
| 2 | M2 | Does the system run normally on both cores with the watchdog page protected? | Fix before starting the heap work - it is the same mechanism underneath. |
| 3 | M6 | Is coverage measurable and are there zero false positives under stress? | Keep the feature opt-in rather than enabled by default in debug builds. |

On Gate 1:  This is the gate that matters most. It is placed deliberately before any investment in the watchdog or the heap, so that a negative answer costs days rather than weeks.

# 10. Patch Structure

How the work is split for review matters as much as the technical sequencing. The previous change was delivered as one large commit spanning architecture code, kernel code, linker scripts and configuration - difficult to review as a whole and impossible to bisect afterwards.

The rule for this work: every commit is independently reviewable and leaves the tree in a working state.

| # | Commit | Touches | Reviewed by |
| --- | --- | --- | --- |
| 1 | Add page-level protect and unprotect primitive (backported where upstream helpers fit) | Architecture code only, no callers | MMU reviewer |
| 2 | Decode and report data abort details, and fix the faulty fault status macro (finding 6) | Data abort handler, architecture header | Anyone |
| 3 | Add memory protection test application | Applications only | Anyone |
| 4 | Group watchdog static data into a single page | Watchdog module, linker script | Kernel reviewer |
| 5 | Raise pre-allocated watchdog timer count | Configuration only | Trivial |
| 6 | Enable page protection for watchdog data | Watchdog module only | Kernel reviewer |
| 7 | Protect large free blocks on release | Heap release and allocate paths | Memory manager reviewer |
| 8 | Handle protection across block merge and split | Heap manager | Memory manager reviewer |
| 9 | Skip protected ranges in heap walkers | Heap diagnostics | Memory manager reviewer |
| 10 | Enable the feature on the reference debug configuration | Configuration only | Trivial |

Nobody has to hold ten files in mind at once, and a bisect months later returns a precise answer rather than a large commit.

## 10.1 One rule to enforce from commit one

Keep the mechanism board-agnostic from the very first commit. The previous attempt hard-coded a physical address and modified a source file shared by every ARM board while referencing a linker symbol that only one board defines. Any other board enabling the feature would fail to link.

Use linker symbols and configuration guards from the start. It costs nothing now and is painful to retrofit later.

# 11. Test Plan

Testing is planned per milestone, not deferred to a final phase. Each test is written alongside the milestone it validates.

| Test | Milestone | What it proves |
| --- | --- | --- |
| Mapping-split equivalence unit test | M0 | All 256 new page entries behave identically to the original mapping |
| Deliberate corruption test application | M0 | The fault fires and the report identifies the instruction and task |
| Performance benchmark, split versus unsplit | M0 | Retires R3 - the heap feature is viable |
| Write from the second core | M2 | Covers exactly what broke the first attempt |
| Timer soak test under load | M2 | Write windows are not leaking and timer behaviour is unchanged |
| Mixed-size allocate and free stress, several hours | M4 | Block merging and splitting are handled correctly |
| Heap information and crash dump with protection enabled | M5 | No self-inflicted faults from our own diagnostics - including the node dump inside the existing detector and the neighbour dump inside the free node assertion macro |
| Coverage counters visible in the log | M6 | The fraction of blocks actually protected is known, not assumed |
| Existing poison detector enabled at the same time | M3 | The two detectors coexist without faulting on each other - see finding 1 |

Worth knowing:  The reference configuration in the earlier change already enables a test application symbol for this feature - but no such configuration entry exists anywhere in the tree and the application was never written. A test application was clearly intended and did not land. Make it a first-class deliverable this time. It is what will be demonstrated, and what proves every later milestone.

## 11.1 Coverage must be measurable

Add counters for blocks protected, blocks skipped because they were too small or badly aligned, and requests that failed because the page-table pool was exhausted. Print them on demand.

Without this, some blocks silently receive no protection while the code assumes they are covered. A corruption then slips through and time is lost asking why the feature did not catch it. The counters make coverage visible rather than assumed.

# 12. Deliberately Out of Scope for Version One

Each of these is defensible later. Each doubles the surface area now. Resist all of them until the core has shipped and is proven.

| Deferred item | Why it can wait |
| --- | --- |
| Quarantine of freed blocks | Improves detection odds but adds allocator policy and heap headroom questions |
| Guard pages around buffers | A separate feature using the same primitive - add once the primitive is trusted |
| Protecting regions beyond the watchdog page and heap free blocks | Easy to add later; each new region needs its own accessor analysis |
| More than one heap | Start with a single heap; extending is mechanical once the pattern works |
| Platforms with a protection unit rather than a full MMU | Different constraints entirely - a separate design |
| Any attempt to cover corruption caused by direct memory access hardware | The MMU cannot see it. Requires hardware this device does not have. |

A working detector for one heap beats a half-working one for four. Ship narrow, then extend.

# 13. Parallel Work

If more than one engineer is available, these tracks are genuinely independent and can start on day one.

| Track | Work | Depends on |
| --- | --- | --- |
| A | Page protect primitive - the architecture half of M0 | Nothing |
| B | Fault decoding, region registry and report - the reporting half of M0 | Nothing |
| C | Test application and benchmark harness | Nothing |
| D | Audit of every existing code path that reads free heap memory | Nothing |

All four converge at Gate 1. After that the critical path is single-threaded through M1, M2, M3 and M4, because each builds directly on the one before.

On scheduling:  Calendar estimates are deliberately omitted, because they depend on headcount and on how much other work runs alongside. What can be stated with confidence is the relative shape: M0 is small, M1 and M2 together are moderate, and M4 alone is larger than everything before it combined. Plan the calendar around M4, not around the watchdog.

# 14. Recommended Order - Summary

| Step | Milestone | Size | Exit criteria |
| --- | --- | --- | --- |
| 1 | M0 - Walking skeleton on a dummy page, plus performance measurement | Small | Split verified entry by entry; a deliberate bad write produces a report naming the instruction, task and address; performance cost measured and accepted |
| 2 | M1 - Watchdog data packing, behaviour-neutral | Small | System boots and runs; timers behave identically; the increased timer count is available; the page cannot overflow (build-time assertion) |
| 3 | M2 - Watchdog protection | Moderate | Runs normally on both cores; an external write to the page is caught and reported; no window is opened around a read |
| - | DECISION POINT - detection technology and page table budget settled with the requester | - | Questions 7, 8 and 9 in appendix B answered |
| 4 | M3 - Heap release and allocate paths only | Moderate | Allocate a large block, release it, write to it, and receive a use-after-free report |
| 5 | M4 - Heap merge, split, reallocate, aligned allocate, deferred list | LARGE | Hours of mixed-size stress with no faults originating inside the allocator |
| 6 | M5 and M6 - Audit and hardening | Moderate | Heap information and crash dumps work with protection enabled; coverage counters reported |

## 14.1 The change from the original instinct

The instinct to do the watchdog before the heap is correct and is kept. The only change this plan proposes is inserting M0 in front of it.

The reason: when the watchdog rework begins, it should be applying a mechanism that is already proven rather than debugging the mechanism and the integration at the same time. That single separation is what turns the first attempt from a setback into groundwork.

Steps 1 to 3 together form a coherent first delivery: a working demonstration, a real subsystem protected, and every line of the foundation carrying straight into the heap work that follows.

# Appendix A - Milestone Checklist

A condensed checklist for tracking progress.

| Milestone | Done when |
| --- | --- |
| M0 architecture | Split, set permission, save and restore implemented behind a generic interface; unit test passes |
| M0 reporting | Fault status and address decoded; region registry in place; report prints instruction, task, address and region |
| M0 test | Test application triggers a deliberate violation and the report is correct |
| M0 measurement | Benchmark run before and after splitting; result recorded and accepted |
| GATE 1 | All four of the above complete and reviewed |
| M1 | Four watchdog globals in one 4 KB page; explicit clearing; timer count raised; build-time size assertion added |
| M2 | Windows at correct call sites; none around reads; closed around callbacks; second-core write test passes |
| GATE 2 | System stable on both cores with protection enabled |
| M3 | Release and allocate paths hooked; use-after-free demonstrated on a large block |
| M4 | Merge, split, reallocate, aligned allocate and deferred list all handled; stress test clean |
| M5 | Every reader of free heap memory audited and fixed |
| M6 | Coverage counters reported; documentation updated |
| GATE 3 | Zero false positives under stress; decision taken on enabling by default |

# Appendix B - Open Questions

These remain scope decisions for the requester and should be settled before the corresponding milestone begins.

| # | Question | Needed by |
| --- | --- | --- |
| 1 | Read-only or no-access for released heap blocks? No-access also catches stale reads but will fault any diagnostic that scans free memory. | M3 |
| 2 | Is quarantine of released blocks in scope? Without it the detection window can be very short on a busy heap. | M4 |
| 3 | Which heaps are covered - kernel, user, external memory, or all? | M3 |
| 4 | Is it understood that double release is already detected in software today, and that the value here is stale-pointer access? | Before M3 |
| 5 | Is the effective minimum block size of roughly twelve kilobytes acceptable, given that four kilobytes cannot be met exactly? | Before M3 |
| 6 | Should the same mechanism be offered later for other rarely written kernel data? | After M6 |
| 7 | Page protection, the upstream sanitiser, or both? The upstream option covers all sizes but needs compiler instrumentation with real size and speed cost. See section 5.1. | BEFORE M3 |
| 8 | Use the four kilobytes of page table slack, or increase the reservation? This caps protectable address space at four megabytes against a heap of roughly sixty. See finding 3. | DURING M0 |
| 9 | How should page protection coexist with the existing poison detector - complementary by size, or mutually exclusive? See finding 1. | BEFORE M3 |
| 10 | Is the permanent divergence from the upstream watchdog design acceptable, given that the memory being protected does not exist upstream? See section 5.3. | BEFORE M1 |